## Sheet1
Description | Launch Blocking | Bug or Feature? | Severity / Impact (High, Medium, Low) | Complexity (High, Medium, Low) | Status (Accepted, Staged, Fixed, Won't Fix) | Owner | Schedule | Notes | Tags (Comma seperated)
When hospitals are deleted, users assigned to that hospital are orphaned (no longer refereced by any hospital). Need to work out how to give them the option to add to a new hospital or just not allow a hospital with staff still assigned to be deleted. | No | Bug | High | Medium | KINDA FIXED (hospitals cannot be deleted if they have staff assgned to them) | Benjamin Reynolds | By R2 Beta | Create option on their homepage maybe to add to hospital. Also on the admin page could use something like the patient admit button to add them to a hospital if they dont belong to one
Date Pick does not work if more than 1 hospital is created and you try to use it with another hospital. Basically same problem as before with them not being unique each time | No | Bug | Medium | High | KINDA FIXED ( moved create doctor and create nurse out of the hospital to have only one instance.) | Benjamin Reynolds | By R2 Beta
Admin homepage is always available at /admin even if no user is logged in or the current user is not an admin | Yes | Bug | Medium | Low | FIXED | Daniel Hoffman | By R2 Beta |  | Admin, Users, Views
Admin user management page does not show users in list; list is blank | No | Bug | Medium | Medium | FIXED | Daniel Hoffman | By Full Release
Admins can create hospitals | Yes | Feature | High | Low | FIXED | Daniel Roberts | By R2 Beta
Allow editing/deleting appointment when clicking on appointment day on calendar | Yes | Feature | High | Medium | Fixed | Jacob Kenin | By R2 Beta
Calendar shows appointments for all users instead of just the logged in user | Yes | Bug | High | High | FIXED | Daniel Hoffman | By R2 Beta |  | Calendar, Models
Cannot assign patients to doctors | Yes | Feature | High | Low | FIXED | Benjamin Reynolds | By R2 Beta
Change password feature only works for patients | Yes | Bug | High | Medium | FIXED | Daniel Roberts | By R2 Beta
Change user password gives no feedback to user and redirects to wrong page, should direct to user edit | No | Feature | Medium | Low | FIXED | Daniel Roberts | By full release | Needs more checks on validity and can use green text boxes like on create account for user feedback | edit account, change password, User
Clicking on an appotinment in the calendar view should bring to the edit appointment page for the appointment | No | Feature | High | Medium | Fixed | Jacob Kenin | By R2 Beta
Clicking the 'Create Account' button on the log out page causes the site to crash | No | Bug | Medium | Low | FIXED | Daniel Hoffman | By R2 Beta | Throws ValueError
Clicking the 'log in' button on the log out page causes the site to crash | No | Bug | Medium | Low | FIXED | Daniel Hoffman | By R2 Beta | Throws UnboundLocalError
Create Account crashes if date field is left empty or is not in the correct format | Yes | Bug | Medium | Medium | FIXED | Daniel Hoffman | By R2 Beta | No longer an issue | Make Account, Forms
Create Account crashes if SSN is non-numeric | Yes | Bug | Medium | Low | FIXED | Daniel Hoffman | By R2 Beta | Consider storing in charfield | Create User, Forms
Create Account crashes if user is not unique | Yes | Bug | Medium | Medium | FIXED | Daniel Hoffman | By R2 Beta | Occurs even if previous user creation failed | Create User, Forms
Create account date time picker is not clickable | No | Bug | Low | Low | FIXED | Daniel Hoffman | By R2 Beta |  | Create Account, Views
Create account link on logout redirect page produces error | No | Bug | Low | Low | FIXED | Daniel Hoffman
date picker on create account does not go past 1970 on create account | No | limitation | medium low | high | FIXED | Benjamin Reynolds | By R2 Beta | change dateime picker | datetimepicker, create account, widgits
Delete appointment view allows viewing and deleting ANYONE'S appointment | No | Bug | High | Medium | FIXED | Jacob Kenin | By R2 Beta | Needs the ability to add doctors, so waiting for Dan
Display appointments in calendar view | Yes | Feature | High | Medium | Fixed | Benjamin Reynolds | By R2 Beta
Doctor and nurse need to have their own home pages. This means is_doctor and is_nurse need to work correctly | Yes | Feature | High | medium | FIXED | Daniel Roberts | By R2 Beta
Doctor information is not completely filled out on account creation | No | Bug | Medium | Medium | Fixed | Jacob Kenin | By R2 Beta |  | Doctor, homepage, models, forms
Extra log in page does not seem to be used | No | Bug | Low | Low | FIXED | Daniel Roberts | By full release | This page is in fact used if the log in fails | Log in, Views
Guarantee all the url names are lowercase | No | Bug | Low | Low | FIXED | Daniel Hoffman
Make Account crashes if passwords are not equal | Yes | Bug | Medium | Low | FIXED | Daniel Hoffman | By R2 Beta |  | Make Account, Forms, Models
Make Appointment crashes when submit is pressed | Yes | Bug | High | Medium | FIXED | Daniel Hoffman | By R2 Beta |  | Make Appointment, Views
Make Appointment, Edit Appointment, and Delete Apointment pages are titled as "Create Account" on browser tab | No | Bug | Low | Low | FIXED | Daniel Hoffman | By R2 Beta |  | Make Account, Make Appointment, Edit Appointment, Delete Appointment, Views
On the manage users page, we display their username. We should display their name in parenthesis next to it, to make it easier to identify people. | Yes | Bug | Medium | Low | FIXED | Daniel Roberts | By R2 Beta
On the patient account edit page, the broswer tab displays 'Health Net Home' | No | Bug | Low | Low | FIXED | Daniel Hoffman
User's first and last name are not formatted with the first letter capitolized and the rest lowercase | No | Bug | Low | Low | FIXED | Daniel Hoffman | By full release |  | Make Account, Forms, Models
When a Doctor is not selected for an appointment and submit is clicked, an error is not returned | No | Bug | Medium | Low | FIXED | Daniel Hoffman | By R2 Beta
Whenever an account is created, upon initial logon the system states that the account was not created properly | Yes | Bug | High | Medium | FIXED | Daniel Roberts | By R2 Beta
If an admin clicks 'make appointment' on the calendar page the site crahses | No | Bug | Medium | Medium | FIXED |  | By R2 Beta | Throws "AttributeError at /make_appointment" "'str' object has no attribute 'is_patient'" | Admin, Views, Calendar, Make Appointment
Make appointment on the view calendar page for the admin page, returns an erro | Yes | Bug | Medium | High | FIXED |  | By R2 Beta
The datepicked does not work for selecting times | Yes | Bug | High | Low | FIXED |  | By R2 Beta
Transferring a doctor yields a 500 error | Yes | Bug | High | Medium | FIXED |  | By R2 Beta
Nurses cannot create appointments | No | Bug | Medium | Medium | FIXED |  | By R3
Add ability to upload a document of medical info with title, description, wether its released or not, and then the file itself | Yes | Feature | Medium | High | Accepted | Benjamin Reynolds / Jacob Kenin | By R2 Beta | A doctor or nurse should be able to click 'add a document' on a patients edit_page and be brought to a page that has a field for title, description, and the file, and wether or not its released or not. Make a model for Documents, and each document is tied to a patient.
Clicking on a user on the admin control panel should bring you to the view user page for them, where you can edit their info | Yes | Feature | Medium | High | Accepted | Jacob Kenin | By R2 Beta | Refactor the edit_account in to a single view, and create a view_user view to allow viewing information about a specific user. Needs the full functionality on the view staff page to be done.
The make appointment, update appointment, and cancel appointment links direct to patient homepage regardless of what type of user is logged in after form submission | Yes | Bug | Medium | Medium | Accepted | Jacob Kenin | By R2 Beta
Duplicate times shown when clicking on the date in the calendar | Yes | Bug | Low | Low
EVERY SINGLE PAGE ON THE SITE INCORRECTLY IMPORTS THE BOOTSTRAP JS LIBRARY. The <script> tag merely points at the resource, but does not specify it as source | No | Bug | High | Low |  |  | Eventually | All you need to do is to go to every page (becuase we don't use template inheritance) and replace the line that imports the bootstrap JS with "<script src="{% static 'js/bootstrap.min.js' %}"></script>"
If an invalid date is entered in Make Appointment or Edit Appointment, it auto-sets to the current date time | No | Bug | Medium | Medium | Won't Fix | Daniel Hoffman | By R2 Beta | Not a bug | Make Appointment, Edit Appointment, Forms, Calendar
Make appointment and change appointment do not check if appointment slot is already taken before accepting appointment | No | Bug | Medium | Medium |  |  | By R2 Beta
Patient's should be able to have at max a 45 min appt, and doctor's can set the length to be as long as they want | Yes | Feature | High | Medium
When a the create account page is filled out with invalid information, it shows an error, but still creates a user | No | Bug | Medium | Medium |  |  | By Full Release
Year View does not display months correctly on calendar | No | Bug | Medium | Medium |  |  | By full release |  | Calendar, Views
You can open multiple tabs for adding medical staff | No | Bug | Low | Low
Second line of address for creating a hospital should not be required | No | Bug | Low | Low
On the homepage the "Create Account" button doesn't work in Internet Explorer | Yes | Bug | High | Medium
When you leave all of the fields blank on the create a doctor page and press submit, no error is show, but it handles correctly | No | Bug | Low | Low
If passwords do not match or phone number is non-numeric on Create Nurse, no HTTP response is given | No | Bug | Medium | Medium
Submitting a blank create admin form doesn't return a HTTPResponse | No | Bug | Medium | Medium
On the edit account page as a patient, the cancel button doesn't work in IE | No | Bug | Low | Low
As anything but an admin, the transfer patient button does not work | Yes | Bug | Medium | Medium